## Sheet1
Tasks Listed by their priority | Affiliated Engineers | Time Budget | Evaluation
GUI Implementation | Amir Sandoval/David Scianni/Steven Shaginyan | April 23rd
GUI Design | David Scianni/Amir Sandoval/Steven Shaginyan | April 18th
Database | Vanik Gevorgyan/Steve Shaginyan | May 8th
Website Update | Vanik Gevorgyan | weekly
Facebook Update | Alec Shay | weekly
Twitter Update | Amir Sandoval | weekly
Prototyping classes | Alec Shay / Sung Jin Park | April 20th
Implementing the BB and Events | Sung Jin Park/Steven Shaginyan/Alec Shay | May 1st
Testing | Sung Jin Park | May 22nd
Managing/Putting it all together | David Scianni | weekly
GUI Upkeep | Amir Sandoval/David Scianni | May 8th
User Elements | Alec Shay/David Scianni | May 8th
UML | David Scianni/Vanik Gevorgyan | April 15th
Notifications | Vanik Gevorgyan | April 30th
Location Services | Vanik Gevorgyan/Steven Shaginyan | May 8th